## Timeline
Category | Task | Start week | Length | Meetings | Weeks
Coding | Setup gRPC, freud and a basic infrastructure to work on (VMs, repo, ...) | 0 | 1 | 2021-02-17 | 0 | 2021-02-15
Coding | Basic toy example with gRPC | 0 | 1 | 2021-02-24 | 1 | 2021-02-22
Coding | Basic hardcoded instrumentation on the example | 1 | 1 | 2021-03-03 | 2 | 2021-03-01
Coding | Add parameter-dependant complexity (loop 10 RPC calls and malloc) | 2 | 1 | 2021-03-10 | 3 | 2021-03-08
Coding | Print memory usage and execution timestamps | 2 | 1 |  | 4 | 2021-03-15
Coding | Produce performance traces (txt files with timestamps) | 3 | 1 | 2021-03-26 | 5 | 2021-03-22
Coding | Associate server-side executions with an ID to send to the client | 3 | 1 |  | 6 | 2021-03-29
Coding | Optimize compilation and installation, add cross-platform instructions | 4 | 1 | 2021-04-09 | 7 | 2021-04-05
Coding | Improve performace traces format to make it compatible with freud-statistics | 5 | 3 |  | 8 | 2021-04-12
Coding | Improve instrumentation functions to pass feature object (key/value) | 5 | 1 |  | 9 | 2021-04-19
Coding | Develop a tool to merge the performance logs from client and server | 5 | 1 |  | 10 | 2021-04-26
Coding | Dockerize the server to easily have it running permanently [non-essential] | 6 | 1 |  | 11 | 2021-05-03
Coding | Develop a reader tool to "decrypt" the traces (with flag for human-readable stamps) [non-essential] |  |  |  | 12 | 2021-05-10
Report | Start on the report template |  |  |  | 13 | 2021-05-17
Coding | Integrate said unified trace in the existing statistics tool (freud-statistics) |  |  |  | 14 | 2021-05-24
Other | Identify some third-party non-trivial distributed applications and analyze them |  |  |  | 15 | 2021-05-31
Report | Write the report, prepare the poster and presentation |  |  |  | 16 | 2021-06-07
Other | Have a pizza |  |  |  | 17 | 2021-06-14
[5 empty] | 18 | 2021-06-21