## Timeline
Category | Status | Task | Start week | Length | End week | Weeks |  | Meetings | Deadlines
Coding | Done | Setup gRPC, freud and a basic infrastructure to work on (VMs, repo, ...) | 0 | 1 | 1 | 0 | 2021-02-15 | 2021-02-17
Coding | Done | Basic toy example with gRPC | 0 | 1 | 1 | 1 | 2021-02-22 | 2021-02-24
Coding | Done | Basic hardcoded instrumentation on the example | 1 | 1 | 2 | 2 | 2021-03-01 | 2021-03-03 | 07.Mar: Title and description (projectDescription.pdf)
Coding | Done | Add parameter-dependant complexity (RPC calls and malloc) | 2 | 1 | 3 | 3 | 2021-03-08 | 2021-03-10
Coding | Done | Print memory usage and execution timestamps | 2 | 1 | 3 | 4 | 2021-03-15 | -
Coding | Done | Produce performance traces (txt files with timestamps) | 3 | 1 | 4 | 5 | 2021-03-22 | 2021-03-26
Coding | Done | Associate server-side executions with an ID to send to the client | 3 | 1 | 4 | 6 | 2021-03-29 | -
Coding | Done | Simplify compilation and installation, add cross-platform instructions | 4 | 1 | 5 | 7 | 2021-04-05 | 2021-04-09 | 11. Apr: Progress report (planningGraph.pdf)
Coding | Done | Improve instrumentation functions to pass arbitrary features | 5 | 1 | 6 | 8 | 2021-04-12 | 2021-04-16
Coding | Done | Develop a tool to merge the performance logs from client and server | 5 | 5 | 10 | 9 | 2021-04-19 | -
Coding | Done | Dockerize the server to easily have it running permanently [non-essential] | 6 | 1 | 7 | 10 | 2021-04-26 | 2021-04-28
Coding | On hold | Develop a reader tool to "decrypt" the traces [non-essential] | 10 | 2 | 12 | 11 | 2021-05-03 | 2021-05-07
Coding | TODO | Integrate the unified trace in the existing statistics tool (freud-statistics) | 10 | 2 | 12 | 12 | 2021-05-10 | 2021-05-14
Other | TODO | Identify some third-party non-trivial distributed applications and analyze them | 13 | 1 | 14 | 13 | 2021-05-17 | 2021-05-21
Report | TODO | Write the report | 11 | 3 | 14 | 14 | 2021-05-24 | 2021-05-28
Other | TODO | Have a pizza | 14 | 1 | 15 | 15 | 2021-05-31 |  | 30. May: Progress report (statusReport.pdf) and report draft
[6 empty] | 16 | 2021-06-07
[6 empty] | 17 | 2021-06-14
[6 empty] | 18 | 2021-06-21 |  | 25. Jun: final report